## Procedures_Rev. 0
|  |  | Documentation / Forms Generation Report | [5 empty] | Document Type |  |  | Procedure |  |  | Aspects /Impacts |  |  |  | PRPs |  | STATUS OF COMPLIANCE
[12 empty] | Work Instructions |  |  | Hazards/ Risks |  |  |  | <others>
[12 empty] | Quality Plans |  |  | HACCP |  |  |  | <others> |  | Docs. Accomplished |  |  | 25 |  |  |  | No. of Docs. | No. of Docs. Drafted | No. of Docs. Endorsed
|  |  | CLIENT |  |  | Romblon State University |  |  |  | CONTACT PERSON |  |  | Dr. Rey Ramos (ISO Facilitator) | [7 empty] | No. of Pending Docs. |  |  | 32
[10 empty] | CONTACT DETAILS | [7 empty] | rsu.plandev2016@gmail.com |  |  | Total Documents |  |  | 57
|  |  | ADDRESS |  |  | Odiongan, Romblon | [6 empty] | TEL. NO./S |  |  | FAX NO./S |  | E-MAIL ADDRESS |  |  | % of Accomplishment |  |  | 43.86%
[10 empty] | CONSULTANTS |  |  | Eric Vinluan | [7 empty] | Status updated as of |  | 2019-03-08
No. | Document No. |  |  | Responsible Dept. |  |  | Document / Form Title | [6 empty] | Date of coaching / initial drafting |  |  | Checking of Reviewed Docs & Coaching of DRRF & List of Records |  | Final Documentation Checking | Registration |  | Document Distribution |  |  | Status |  | CONSULTANT
DOCUMENT CONTROLLER
[7 empty] | CONTROL OF DOCUMENTED INFORMATION | [6 empty] | March 29, 2019 | [10 empty] | March 29, 2019: Already endorsed a draft procedure |  | Aian | 1
ISO FACILITATOR
[7 empty] | MANAGEMENT REVIEW PROCEDURE | [6 empty] | March 29, 2019 | [10 empty] | March 29, 2019: Already endorsed a draft procedure |  | Rico | 1
[7 empty] | CORRECTIVE ACTION PROCEDURE | [6 empty] | March 29, 2019 | [10 empty] | March 29, 2019: Already endorsed a draft procedure |  | Rico | 1
[7 empty] | INTERNAL AUDIT PROCEDURE | [6 empty] | 2019-01-25 |  |  | 2019-03-07 | [7 empty] | Checked the presented procedure and coached its finalization |  | Rico | 1 | 1
[7 empty] | RISK AND OPPORTUNITIES PROCEDURE | [6 empty] | March 29, 2019 | [10 empty] | March 29, 2019: Already endorsed a draft procedure |  | Rico | 1
[7 empty] | CONTROL OF NONCONFORMING OUTPUT PROCEDURE | [6 empty] | March 29, 2019 | [10 empty] | March 29, 2019: Already endorsed a draft procedure |  | Rico | 1
[7 empty] | CUSTOMER SATISFACTION CONTROL PROCEDURE | [6 empty] | March 29, 2019 | [10 empty] | March 29, 2019: personnel not available during the visit, endorsed procedure |  | Aian | 1
[7 empty] | HANDLING CUSTOMER COMPLAINTS PROCEDURE | [6 empty] | March 29, 2019 | [10 empty] | March 29, 2019: personnel not available during the visit, endorsed procedure |  | Aian | 1
Admission, Accreditation and Faculty Evaluation
[7 empty] | ADMISSION AND REGISTRATION PROCEDURE | [6 empty] | 2019-03-07 |  |  | March 26, 2019 | [7 empty] | Coached the preparation of the procedure |  | Eric | 1 | 1
[7 empty] | ACCREDITATION PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 29, 2019: personnel not available during the visit |  | Eric | 1 | 1
[7 empty] | FACULTY EVALUATION PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 29, 2019: personnel not available during the visit |  | Eric | 1 | 1
REGISTRAR
[7 empty] | HANDLING OF STUDENT RECORDS | [6 empty] | March 7, 2019 |  |  | March 25, 2019 | [7 empty] | Checked the presented procedure and coached its finalization |  | RICO | 1 | 1
ACADEMIC AFFAIRS (Delivery Instruction)
[7 empty] | DEVELOPMENT OF PROGRAMS PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit |  | Eric | 1 | 1
[7 empty] | DESIGN AND DEVELOPMENT OF CURRICULUM AND SYLLABUS PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit |  | Eric | 1 | 1
[7 empty] | PROMOTION OF PROGRAM OFFERINGS PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit, to be endorsed to media |  | Eric | 1 | 1
[7 empty] | CLASSROOM MANAGEMENT PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit |  | Eric | 1 | 1
[7 empty] | ASSESSMENT OF STUDENTS PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit |  | Eric | 1 | 1
[7 empty] | RETENTION OF STUDENTS CONTROL PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit |  | Eric | 1 | 1
[7 empty] | STUDENT EVALUATION FOR GRADUATION AND PROMOTION PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit |  | Eric | 1 | 1
[7 empty] | GRADUATION OF STUDENTS AND CONFERMENT OF DEGREES PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 25, 2019: A corrections are required during the audit |  | Eric | 1 | 1
[7 empty] | DELIVERY OF INSTRUCTION (IMPLEMENTATION OF OJT/INTERNSHIP) CONTROL PROCEDURE | [9 empty] | March 26, 2019 | [7 empty] | March 25, 2019: A corrections are required during the audit |  | Aian | 1
[7 empty] | IMPLEMENTATION OF FIELD TRIPS PROCEDURE | [17 empty] | March 25, 2019: A corrections are required during the audit |  | Aian | 1
INSTITUTE OF GRADUATE STUDIES
[7 empty] | GUIDELINE AND STANDARD FOR MASTER'S THESIS AND DISSERTATION PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | Checked the presented procedure and coached its finalization |  | Eric | 1 | 1
PLANNING
[7 empty] | STRATEGIC PLANNING CONTROL PROCEDURE | [6 empty] | March 28, 2019 | [10 empty] | March 28, 2019: Already checked the drafted procedure |  |  | 1
[7 empty] | MONITORING AND EVALUATION CONTROL PROCEDURE | [17 empty] | March 28, 2019: No draft during the visit |  |  | 1
BAC
[7 empty] | BAC CONTROL PROCEDURE | [6 empty] | March 8, 2019 |  |  | March 27, 2019 | [7 empty] | Coached the preparation of the procedure |  | RICO | 1
SUPPLY
[7 empty] | SUPPY MANAGEMENT CONTROL PROCEDURE | [6 empty] | March 7, 2019 |  |  | March 27, 2019 | [7 empty] | Coached the preparation of the procedure |  | RICO | 1
[7 empty] | PROCURMENT CONTROL PROCEDURE | [6 empty] | March 7, 2019 |  |  | March 27, 2019 | [7 empty] | Coached the preparation of the procedure |  | RICO | 1
[7 empty] | EXTERNAL PROVIDER ACCREDITATION AND PERFORMANCE EVALUATION PROCEDURE | [6 empty] | March 7, 2019 |  |  | March 27, 2019 | [7 empty] | Coached the preparation of the procedure |  | RICO | 1
[7 empty] | CALIBRATION CONTROL PROCEDURE | [6 empty] | March 8, 2019 | [10 empty] | March 29, 2019: draft has been endorsed, no process owner |  | RICO | 1
HR (Faculty/Staff Development)
[7 empty] | HUMAN RESOURCE MANAGEMENT CONTROL PROCEDURE | [6 empty] | 2019-03-08 |  |  | March 27, 2019 | [7 empty] | March 28, 2019: Checked the presented procedure and coached its finalization |  | RICO | 1
[7 empty] | REWARDS AND RECOGNITION CONTROL PROCEDURE | [6 empty] | 2019-03-08 |  |  | March 27, 2019 | [7 empty] | March 29, 2019: Checked the presented procedure and coached its finalization |  | RICO | 1
|  |  |  | no |  |  | COMPETENCE, TRAINING & AWARENESS CONTROL PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | Coached the preparation of the procedure |  | Eric | 1
|  |  |  | no |  |  | CONTROL OF POSITION DESCRIPTION AND TABLE OF ORGANIZATION PROCEDURE | [6 empty] | 2019-03-08 | [10 empty] | Coached the preparation of the procedure |  | Eric | 1
[7 empty] | HANDLING GRIEVANCE CONTROL PROCEDURE | [6 empty] | March 27, 2019 | [10 empty] | March 29, 2019: Checked the presented procedure and coached its finalization |  | RICO
[7 empty] | STRATEGIC PERFORMANCE MANAGEMENT PROCEDURE | [6 empty] | March 27, 2019 | [10 empty] | March 29, 2019: Checked the presented procedure and coached its finalization |  | RICO
[7 empty] | PAYROLL AND REMITTANCE CONTROL PROCEDURE | [6 empty] | March 27, 2019 | [10 empty] | March 29, 2019: Checked the presented procedure and coached its finalization |  | RICO
BUDGET
[7 empty] | BUDGET PREPARATION PROCEDURE | [6 empty] | March 27, 2019 | [10 empty] | March 27, 2019: flow charting corrections, inclusion of campus interface |  | AIAN | 1
[7 empty] | BUDGET EXECUTION PROCEDURE | [6 empty] | March 27, 2019 | [10 empty] | March 27, 2019: flow charting corrections, inclusion of campus interface |  | AIAN | 1
[7 empty] | FINANCIAL ACCOUNTABILITY PROCEDURE | [6 empty] | March 27, 2019 | [10 empty] | March 27, 2019: flow charting corrections, inclusion of campus interface |  | AIAN | 1
CASHIER
[7 empty] | CASHIERING CONTROL PROCEDURE | [6 empty] | March 7, 2019 |  |  | March 25, 2019 | [7 empty] | Checked the presented procedure and coached its finalization |  | RICO | 1 | 1
FINANCIAL MANAGEMENT & SERVICES
[7 empty] | DISBURSEMENT CONTROL PROCEDURE | [6 empty] | March 7, 2019 | [10 empty] | March 27, 2019: Include process for the satellite campuses |  | AIAN | 1 | 1
[7 empty] | BANK RECONCILIATION CONTROL PROCEDURE | [6 empty] | March 7, 2019 | [10 empty] | March 27, 2019: Include process for the satellite campuses |  | AIAN | 1
[7 empty] | PREPARATION OF FINANCIAL STATEMENT CONTROL PROCEDURE | [6 empty] | March 7, 2019 | [10 empty] | March 27, 2019: Include process for the satellite campuses |  | AIAN | 1
PRODUCTION
[7 empty] | RSU INCOME GENERATING PROJECT IMPLEMENTATION PROCEDURE | [6 empty] | March 8, 2019 | [10 empty] | March 29, 2019: Personnel not available |  | RICO | 1
[7 empty] | ACCREDITING UNIVERSITY IGP PROJECTS PROCEDURE | [6 empty] | March 8, 2019 | [10 empty] | March 29, 2019: Personnel not available |  | RICO | 1
STUDENT SERVICES
[7 empty] | ON-CAMPUS ACTIVITIES CONTROL PROCEDURE | [6 empty] | March 7, 2019 |  |  | March 27, 2019 | [7 empty] | March 27, 2019: for finalization |  | RICO | 1 | 1
[7 empty] | OFF-CAMPUS ACTIVIES CONTROL PROCEDURE | [6 empty] | March 7, 2019 |  |  | March 27, 2019 | [7 empty] | March 27, 2019: for finalization |  | RICO | 1 | 1
[7 empty] | ACCREDITATION OF STUDENT ORGANIZATION CONTROL PROCEDURE | [6 empty] | MARCH 7, 2019 |  |  | March 27, 2019 | [7 empty] | March 27, 2019: for finalization |  | RICO | 1 | 1
[7 empty] | DELIVERY OF INSTRUCTION (IMPLEMENTATION OF OJT/ INTERSHIP) CONTROL PROCEDURE | [6 empty] | MARCH 7, 2019 | [10 empty] | Checked the presented procedure and coached its finalization |  | RICO | 1 | 1
[7 empty] | COUNSELING CONTROL PROCEDURE | [6 empty] | March 8, 2019 |  |  | March 27, 2019 | [7 empty] | March 27, 2019: for finalization |  | RICO | 1 | 1
RESEARCH, EXTENSION & TRAINING OFFICE
[7 empty] | RSU EXTENSION CONTROL PROCEDURE | [6 empty] | March 7, 2019 |  |  | March 27, 2019 | [7 empty] | Checked the presented procedure and coached its finalization |  | RICO | 1 | 1
|  |  |  | no |  |  | RSU RESEARCH CONTROL PROCEDURE | [6 empty] | March 7, 2019 | [10 empty] | March 29, 2019: procedure not available duringthe visit |  | RICO | 1
|  |  |  | no |  |  | RSU TRAINING CONTROL PROCEDURE | [6 empty] | March 7, 2019 | [10 empty] | March 29, 2019: procedure not available duringthe visit |  | RICO | 1
AUXILIARY
[7 empty] | MAINTENANCE OF UNIVERSITY EQUIPMENT AND PROPERTY | [6 empty] | 2019-03-07 | [10 empty] | March 29, 2019: procedure not available duringthe visit |  | Eric | 1
[7 empty] | GENERAL SERVICES PROVISION PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 29, 2019: procedure not available duringthe visit |  | Eric | 1
[7 empty] | PROJECT MANAGEMENT PROCEDURE | [6 empty] | 2019-03-07 | [10 empty] | March 29, 2019: procedure not available duringthe visit |  | Eric | 1
LIBRARY
[7 empty] | LIBRARY CONTROL PROCEDURE | [6 empty] | March 8, 2019 |  |  | March 25, 2019 | [7 empty] | Checked the presented procedure and coached its finalization |  | RICO | 1 | 1
MEDICAL / DENTAL
[7 empty] | MEDICAL CONTROL PROCEDURE | [6 empty] | March 8, 2019 |  |  | March 25, 2019 | [7 empty] | Checked the presented procedure and coached its finalization |  | RICO | 1 | 1
[7 empty] | DENTAL CONTROL PROCEDURE | [6 empty] | March 8, 2019 |  |  | March 25, 2019 | [7 empty] | Coached the preparation of the procedure |  | RICO | 1 | 1
GENDER AND DEVELOPMENT
[7 empty] | GENDER AND DEVELOPMENT CONTROL PROCEDURE | [17 empty] | March 29, 2019: no drafted procedure during the visit. |  | RICO
[7 empty] | OFFICE OF THE BOARD SECRETARY | [17 empty] | March 29, 2019: no drafted procedure during the visit. |  | RICO
[7 empty] | BOAD SESSION CONTROL PROCEDURE | [17 empty] | March 29, 2019: no drafted procedure during the visit. |  | RICO
[28 empty] | 57 | 25 | 0
Rev No. |  | Revision Date |  |  | Revision History |  |  | Updated by |  |  |  | UPDATED BY: | [6 empty] | APPROVED BY: | [6 empty] | CONFORMED BY:
ø |  | Mar. 7~8, 2019 |  |  | Initial Documentation Coaching/Gap Analysis |  |  | Eric Vinluan
1 |  | March 25-28, 2019 |  |  | Checking of documents. SWOT, Needs. Risk, Opportunities and Quality Objectives |  |  | Christian John A. Vinluan & Rico Pendon
[11 empty] | Eric Vinluan | [7 empty] | Margel Albano-Jajurie
[12 empty] | MVC Consultant | [6 empty] | MVC President/Principal Consultant | [6 empty] | Client Representative
MVC-OP-002 Effectivity date : December 29, 2015
Note: Initial Drafting - it means procedure is only partially drafted. Concerned department shall continue the completion of the procedure content.
Note on M44: Eric: Covers both Determining the Needs to Offcer New Program/s and the process of Developing the New & Existing Programs
Note on M80: Eric: COVERS: - DETERMINING EQUIPMENT AND SUPPY NEEDS OF DELIVERY UNITS - ISSUANCE OF EQUIPMENT AND SUPPLIES -INVENTORY
Note on M94: Eric: COVERS: - DETERMINING HR TRAINING & SCHOLARSHIP NEEDS - IMPLEMENTATION OF HR DEVELOPMENT THROUGH TRAINING - IMPLEMENTATION OF HR DEVELOPMENT THROUGH SCHOLARSHIPS - TRAINING EVALUATION
Note on M106: Eric: COVERS: - DETERMINING BUDGETARY REQUIREMENTS OF DELIVERY UNITS - DRAWING UP OF UNIVERSITY BUDGET - IMPLEMENTATION AND MONITORING OF UNIVERSITY BUDGET
Note on M108: Eric: COVERS: - DETERMINING BUDGETARY REQUIREMENTS OF DELIVERY UNITS - DRAWING UP OF UNIVERSITY BUDGET - IMPLEMENTATION AND MONITORING OF UNIVERSITY BUDGET
Note on M110: Eric: COVERS: - DETERMINING BUDGETARY REQUIREMENTS OF DELIVERY UNITS - DRAWING UP OF UNIVERSITY BUDGET - IMPLEMENTATION AND MONITORING OF UNIVERSITY BUDGET

## Sheet2
Units | Main Campus | San Fernando | Santa Fe | San Andres | Calatrava | San Agustin | Sta Maria | Romblon | Cajidiocan
Deputy DCC (Campus) | [9 empty] | SWOT | TOP MANAGEMENT RECORD |  |  | DOCUMENTATION RECORD
Deputy ISO Facilitator (Director) | [9 empty] | Needs Expectation | RESPONSIBLE | OUTPUT | TOP | FLOW | RESPONSIBLE | OUTPUT
Admission, Accre | [9 empty] | Risk Assessment | TOP MANAGEMENT (ISO FACILITATOR) | SYSTEM WIDE SWOT |  |  | Process owner (from Diff Campuses) 1 point person (Leader) cover the whole system | Draft Procedure
Registrar | [9 empty] | Opportunities Action Plan |  | SYSTEM WIDE NEEDS AND EXPECTATION
Academic Affairs | [9 empty] | Quality Objective |  | SYSTEM WIDE OPPORTUNITIES ACTION PLAN |  |  | Point person per unit cover whole system | List of records and forms with form number
IGS | [9 empty] | Procedures |  | SYSTEM RISK ASSESSMENT
Planning | [9 empty] | List of Records |  |  |  |  | Process owner (from Diff Campuses) 1 point person cover the whole system | Draft Procedure
BAC | [10 empty] | SATELLITE CAMPUSES | CAMPUS WIDE SWOT
Supply | [10 empty] | DIRECTOR | CAMPUS WIDE NEEDS AND EXPECTATION |  |  | Central DCC | Final Draft of Procedure | Main campus
HR | [10 empty] | VPAA - MAIN CAMPUS | CAMPUS WIDE OPPORTUNITIES ACTION PLAN
Budget | [11 empty] | CAMPUS WIDE RISK ASSESSMENT |  |  | Central DCC | Master Copy | campus DCC
Cash
FMS | [10 empty] | UNITS (PER CAMPUS) | SWOT |  |  | Campus DCC | 1 set Controlled Copy | Process owner (per unit per process)
Production | [11 empty] | NEEDS AND EXPECTATION
Student Service | [11 empty] | OPPORTUNITIES ACTION PLAN |  |  | Process owner (from Diff Campuses) | Specific Controlled Copy for the Unit process
Research Extension | [11 empty] | RISK ASSESSMENT
AUX | [11 empty] | QUALITY OBJECTIVE
Library | [12 empty] | BOTTOM
Medical/ Dental
DCC (Central)
ISO Facilitator (Central)
LEGEND | With in-house office |  |  | No in-campus office
| PLAN A |  |  |  | PLAN B
| Date of Submission of all requirements (1 month before implementation): April 29, 2019 |  |  |  | Date of Submission of all requirements (1 month before implementation): May 27, 2019
| Implementation Date: June 3, 2019 |  |  |  | Implementation Date: June 24, 2019
| Internal Audit (1 month after implementation): July 8-10, 2019 |  |  |  | Internal Audit (1 month after implementation): July 29-31, 2019
| Management review: July 15, 2019 |  |  |  | Management review: August 5, 2019
| Special Internal audit: July 19, 2019 |  |  |  | Special Internal audit: August 9, 2019
| MVC Audit: 4th week of July 2019 |  |  |  | MVC Audit: 4th week of August 2019
| Certification Date Stage 1 audit: 1st week of August 2019 |  |  |  | Certification Date Stage 1 audit: 1st week of September 2019
| Certification Date Stage 2 audit: 2nd week of August 2019 |  |  |  | Certification Date Stage 2 audit: 2nd week of September 2019
Drafting of Procedure
List of Records
Final Draft
Reg. Procedure
MASTER COPY
CONTROLLED COPY
UNIT CONTROLLED COPY
MASTER COPY
CONTROLLED COPY
CONTROLLED COPY (Unit1)
CONTROLLED COPY (Unit 2)
CONTROLLED COPY (Unit 3)

## Main Campus
OUTPUT MATRIX (MAIN CAMPUS)
Units |  | S | N | R | O | QO | List of Records | Forms with Form Number
Admission, Accre
Registrar
Academic Affairs
IGS
Planning
BAC
Supply
HR
Budget
Cash
FMS
Production
Student Service
Research Extension
AUX
Library
Medical/ Dental
GAD
Boardsecretary
Records
DCC (Central) | [5 empty] | N/A
VPAA | [5 empty] | N/A | N/A | N/A
ISO Facilitator (Central) | [5 empty] | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 149
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 0
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 0%
Applicable
Consolidated Output Campus Wide
Consolidated Output System Wide
Applicable for Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## San fernando
OUTPUT MATRIX (San Fernando)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS | [6 empty] | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC | [6 empty] | N/A
Supply | [6 empty] | N/A
HR | [6 empty] | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS | [6 empty] | N/A
Production | [6 empty] | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX | [6 empty] | N/A
Library | [6 empty] | N/A
Medical/ Dental | [6 empty] | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) |  | 1 |  |  |  | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 88
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 1
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 1.136%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## Santa Fe
OUTPUT MATRIX (Santa Fe)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS |  | N/A | N/A | N/A | N/A | N/A | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC |  | N/A | N/A | N/A | N/A | N/A | N/A
Supply |  | N/A | N/A | N/A | N/A | N/A | N/A
HR |  | N/A | N/A | N/A | N/A | N/A | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS |  | N/A | N/A | N/A | N/A | N/A | N/A
Production | [6 empty] | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX |  | N/A | N/A | N/A | N/A | N/A | N/A
Library | [6 empty] | N/A
Medical/ Dental |  | N/A | N/A | N/A | N/A | N/A | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) |  | 1 | 1 | 1 | 1 | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 48
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 4
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 8.333%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## San Andres
OUTPUT MATRIX (San Andres)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS |  | N/A | N/A | N/A | N/A | N/A | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC |  | N/A | N/A | N/A | N/A | N/A | N/A
Supply |  | N/A | N/A | N/A | N/A | N/A | N/A
HR |  | N/A | N/A | N/A | N/A | N/A | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS |  | N/A | N/A | N/A | N/A | N/A | N/A
Production |  | N/A | N/A | N/A | N/A | N/A | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX |  | N/A | N/A | N/A | N/A | N/A | N/A
Library | [6 empty] | N/A
Medical/ Dental |  | N/A | N/A | N/A | N/A | N/A | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) |  | 1 | 1 | 1 | 1 | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 43
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 4
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 9.302%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## Calatrava
OUTPUT MATRIX (Calatrava)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS |  | N/A | N/A | N/A | N/A | N/A | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC |  | N/A | N/A | N/A | N/A | N/A | N/A
Supply |  | N/A | N/A | N/A | N/A | N/A | N/A
HR |  | N/A | N/A | N/A | N/A | N/A | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS |  | N/A | N/A | N/A | N/A | N/A | N/A
Production |  | N/A | N/A | N/A | N/A | N/A | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX |  | N/A | N/A | N/A | N/A | N/A | N/A
Library | [6 empty] | N/A
Medical/ Dental |  | N/A | N/A | N/A | N/A | N/A | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) |  | 1 |  |  |  | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 43
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 1
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 2.326%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## San Agustin
OUTPUT MATRIX (San Agustin)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS |  | N/A | N/A | N/A | N/A | N/A | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC |  | N/A | N/A | N/A | N/A | N/A | N/A
Supply |  | N/A | N/A | N/A | N/A | N/A | N/A
HR |  | N/A | N/A | N/A | N/A | N/A | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS |  | N/A | N/A | N/A | N/A | N/A | N/A
Production |  | N/A | N/A | N/A | N/A | N/A | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX |  | N/A | N/A | N/A | N/A | N/A | N/A
Library | [6 empty] | N/A
Medical/ Dental | [6 empty] | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) | [5 empty] | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 48
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 0
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 0%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## Santa Maria
OUTPUT MATRIX (Santa Maria)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS |  | N/A | N/A | N/A | N/A | N/A | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC |  | N/A | N/A | N/A | N/A | N/A | N/A
Supply |  | N/A | N/A | N/A | N/A | N/A | N/A
HR |  | N/A | N/A | N/A | N/A | N/A | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS |  | N/A | N/A | N/A | N/A | N/A | N/A
Production |  | N/A | N/A | N/A | N/A | N/A | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX |  | N/A | N/A | N/A | N/A | N/A | N/A
Library | [6 empty] | N/A
Medical/ Dental |  | N/A | N/A | N/A | N/A | N/A | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) | [5 empty] | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 43
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 0
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 0%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## Romblon
OUTPUT MATRIX (Romblon)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS | [6 empty] | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC |  | N/A | N/A | N/A | N/A | N/A | N/A
Supply |  | N/A | N/A | N/A | N/A | N/A | N/A
HR |  | N/A | N/A | N/A | N/A | N/A | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS |  | N/A | N/A | N/A | N/A | N/A | N/A
Production |  | N/A | N/A | N/A | N/A | N/A | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX |  | N/A | N/A | N/A | N/A | N/A | N/A
Library | [6 empty] | N/A
Medical/ Dental |  | N/A | N/A | N/A | N/A | N/A | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) |  | 1 | 1 | 1 |  | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 48
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 3
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 6.25%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## Cajidiocan
OUTPUT MATRIX (Cajidiocan)
Units |  | S | N | R | O | QO | List of Records
Admission, Accre | [6 empty] | N/A
Registrar | [6 empty] | N/A
Academic Affairs | [6 empty] | N/A
IGS |  | N/A | N/A | N/A | N/A | N/A | N/A
Planning |  | N/A | N/A | N/A | N/A | N/A | N/A
BAC |  | N/A | N/A | N/A | N/A | N/A | N/A
Supply |  | N/A | N/A | N/A | N/A | N/A | N/A
HR |  | N/A | N/A | N/A | N/A | N/A | N/A
Budget |  | N/A | N/A | N/A | N/A | N/A | N/A
Cash | [6 empty] | N/A
FMS |  | N/A | N/A | N/A | N/A | N/A | N/A
Production | [6 empty] | N/A
Student Service | [6 empty] | N/A
Research Extension | [6 empty] | N/A
AUX |  | N/A | N/A | N/A | N/A | N/A | N/A
Library | [6 empty] | N/A
Medical/ Dental | [6 empty] | N/A
DCC (Campus) | [5 empty] | N/A | N/A
ISO Facilitator (Director) |  | 1 | 1 | 1 | 1 | N/A | N/A
Legend: | S | SWOT Analysis
| N | Needs and Expectation of Interested Party |  |  |  | Total Req. Output: | 53
| R | Risk Assessment Registry
| O | Opportunities Action Plan |  |  |  | Actual Output | 4
| QO | Qualty Objectoves
| N/A | Not Applicable |  |  |  | % Compliance | 7.547%
Applicable
Consolidated Campus Wide
Consolidated System Wide
Unit Point Person (Leader)
| 1 | already accomplished
Rev Status: | Date of Update
0 | March 29, 2019

## Sheet1
san fernando swot analysis
San fe swot analysis
Accounting SWOT Need and |  | Qualty objective
Santafe
SWOT
Needs and Expectation
| Risk Assessment |  | No Critical Process
Opportunities Action
Budget Quality Objective
San Andres
SWOT
Needs and Expectation
| Risk Assessment |  | No Critical Process
Opportunities Action